## Sheet2
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Abnormal Pyschology Assign | 10 | 2 | 0 | 2 | 2 | 0 | 0 | 4 | 10
Database Assign 4 | 12 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 12
IT pert analysis | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
Actual Remaining hours | 26 | 22 | 20 | 16 | 12 | 10 | 8 | 0
Estimated Remaining hours | 26 | 22.5 | 19 | 16 | 12.5 | 9 | 5 | 0

## Sheet3
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Schizophrenia assign | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 12
Database Assign 5 | 14 | 1 | 4 | 1 | 2 | 2 | 2 | 2 | 14
C# Assign 3 | 10 | 4 | 1 | 0 | 1 | 2 | 2 | 0 | 10
Actual Remaining hours | 36 | 29 | 22 | 19 | 14 | 8 | 0 | 0
Estimated Remaining hours | 36 | 30 | 24 | 19 | 13.5 | 8 | 3.5 | 0

## Sheet4
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Database Assign 6 | 11 | 5 | 0 | 0 | 2 | 1 | 2 | 1 | 11
Enterprise Computing Assign-2 Part1 | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 8
Actual Remaining hours | 19 | 12 | 10 | 8 | 4 | 3 | 1 | 0
Estimated Remaining hours | 19 | 15.4 | 12 | 9 | 6.5 | 4 | 1.75 | 0

## Sheet5
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Enterprise Computing Assign-2 Part2 | 12 | 1 | 4 | 2 | 3 | 1 | 1 | 0 | 12
Database project task 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 6
Actual Remaining hours | 18 | 16 | 11 | 8 | 4 | 2 | 0 | 0
Estimated Remaining hours | 18 | 15 | 12 | 9 | 6.5 | 4 | 2 | 0

## Sheet6
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Enterprise Computing Assign-2 Part2 | 12 | 1 | 4 | 2 | 3 | 1 | 1 | 0 | 12
Database project task 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 6
database project task 2 | 10 | 0 | 2 | 3 | 1 | 2 | 2 | 0 | 10
Actual Remaining hours | 28 | 26 | 19 | 13 | 8 | 4 | 0 | 0
Estimated Remaining hours | 28 | 23 | 18 | 13.5 | 9.5 | 6 | 3 | 0

## Sheet7
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Enterprise Computing Assign-2 Part 3 | 12 | 2 | 0 | 2 | 0 | 3 | 2 | 3 | 12
database project task 3 | 10 | 2 | 0 | 2 | 2 | 0 | 2 | 2 | 10
IT project report | 8 | 2 | 0 | 3 | 1 | 2 | 0 | 0 | 8
Actual Remaining hours | 30 | 24 | 24 | 17 | 14 | 9 | 5 | 0
Estimated Remaining hours | 30 | 25 | 21 | 17 | 13 | 9.5 | 5 | 0

## Sheet8
Semester Planning part 2 after midterm | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
GNED final project | 14 | 3 | 0 | 2 | 2 | 0 | 3 | 4 | 14
C# project | 16 | 4 | 2 | 2 | 0 | 3 | 3 | 2 | 16
IT final project | 12 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 12
Actual Remaining hours | 42 | 33 | 31 | 25 | 21 | 16 | 8 | 0
Estimated Remaining hours | 42 | 34.5 | 29 | 23 | 17.5 | 11.5 | 6 | 0

## Sheet10
Semester Planning part 1 | Start hours | Day7 | Day6 | Day5 | Day4 | Day3 | Day2 | Day1 | Total hours
Layout of pages | 8 | 2 | 1 | 0 | 2 | 1 | 2 | 0 | 8
Actual Remaining hours | 8 | 6 | 5 | 5 | 3 | 2 | 0 | 0
Estimated Remaining hours | 8 | 6.5 | 5 | 3.85 | 2.8 | 1.75 | 0.75 | 0

## Sheet11
Semester Planning part 1 | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Advanced database lab | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 5
GNED introduction Assignment | 9 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 9
Actual Remaining hours | 14 | 10 | 5 | 4 | 2 | 0 | 0 | 0
Estimated Remaining hours | 14 | 11 | 8.5 | 6.5 | 4.5 | 3 | 1.5 | 0

## Sheet12
Semester Planning part 1 | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Advanced database Assignment 1 | 7 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 7
C# assignment 1 | 7 | 1 | 0 | 3 | 1 | 1 | 0 | 1 | 7
IT business case | 4 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 4
Actual Remaining hours | 18 | 15 | 12 | 8 | 4 | 2 | 1 | 0
Estimated Remaining hours | 18 | 14.5 | 11.5 | 9 | 6.5 | 4 | 2 | 0

## Sheet13
Semester Planning part 1 | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Advanced database Assign 2 | 10 | 2 | 0 | 2 | 2 | 0 | 0 | 4 | 10
GNED Reflection on clara's ride | 9 | 2 | 2 | 1 | 1 | 2 | 1 | 0 | 9
Actual Remaining hours | 19 | 15 | 13 | 10 | 7 | 5 | 4 | 0
Estimated Remaining hours | 19 | 16 | 13 | 10 | 7.5 | 5 | 2.5 | 0

## Sheet14
Semester Planning part 1 | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
GNED Anxiety ASSIGNMENT | 8 | 1 | 2 | 0 | 1 | 2 | 2 | 0 | 8
C# Assignment 2 | 10 | 3 | 2 | 0 | 1 | 0 | 3 | 1 | 10
.Net Web app Assignment | 5 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 5
Advanced database Assign 3 | 9 | 2 | 1 | 1 | 0 | 2 | 2 | 1 | 9
Actual Remaining hours | 32 | 26 | 21 | 19 | 15 | 9 | 2 | 0
Estimated Remaining hours | 32 | 27 | 22.5 | 18 | 13 | 8.5 | 4 | 0

## Sheet15
Semester Planning part 1 | Start hours | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
burn down diagram IT | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 3
gantt chart IT | 6 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 6
project report IT | 7 | 1 | 0 | 4 | 2 | 0 | 0 | 0 | 7
GNED movie reflection Assignment | 9 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 9
Actual Remaining hours | 25 | 19 | 16 | 10 | 5 | 2 | 1 | 0
Estimated Remaining | 25 | 21 | 17 | 12.5 | 9 | 6 | 3 | 0