## Sheet1
Video Game Website Project | Start hours | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total hours
Layout of pages | 8 | 6 | 2 | 0 | 2 | 1 | 8
Authentication and security protections | 8 | 5 | 3 | 1 | 2 | 2 | 8
javascript,css structures | 9 | 6 | 2 | 2 | 0 | 2 | 9
Regular updates with maintainence | 9 | 7 | 0 | 3 | 1 | 3 | 9
malware protection and compatibility for phones | 7 | 6 | 2 | 1 | 1 | 1 | 7
additional features | 7 | 7 | 0 | 2 | 3 | 0 | 7
Actual Remaining hours | 48 | 37 | 27 | 18 | 9 | 0
Expected Remaining hours | 48 | 26 | 35 | 22 | 9 | 0